## Sheet1
Instructions: •Identified issues and risks/opportunities are examples only - you will need to update/replace them to reflect internal and external issues (as per 4.1 Context of the Organisation) and expectations of interested parties (as per 4.2). •Examples of interested parties are found from row 123 onwards (e.g. clients and workers). •The Results column (Column H onwards) is intended to enable you to record progress on actions (as identified under Column D - Further Actions).
Risk, Opportunity and Objectives Register V1 [Enter Date]
Issue/ Expectation/ Source | Risk/ Opportunity | Related Objectives | Further Actions | Who | By When | Monitoring Method | Result End Quarter 1 Year | Year 1 Q2 | Year 1 Q3 | Year 1 Q4 | Year 2 Q1 | Year 2 Q2 | Year 2 Q3 | Year 2 Q4 | Year 3 Q1 | Year 3 Q2 | Year 3 Q3 | Year 3 Q4
Workflow program | Risks: • Inconsistent work levels • Cashflow – regular income, forecasting • Resources unavailable to schedule works. | • Identify and engage marketing resource • Staff training – upskill in area of business development (1% of budget) | • Develop new marketing material. • Engage new Business Development • Develop business development strategy • Forecasting approach • Staff retention (refer below) • Microsoft project training for resource scheduling • Review lead report in WFM in the Quarterly Management meeting | Operations Manager | New manager - July 2018 Upskilling program – commenced by September 2018 | Review expenditure on BD related training and development
Opportunities: • Marketing resource to increase consistency of workflow • Business development • Target areas
Staff | Risks: • Morale • Poor engagement and productivity • Loss of key staff/ skills/ knowledge. • Retention • Un-safe work environment | · Develop staff retention strategy | • Better communication • Staff input – encourage as part of toolbox talks and site communication • Consider regular Supervisors and Level 3 meetings (and/or more group emails) • Unsafe workplace – supervision, communication, systems | GM | 2018-12-01
Opportunities: • Interesting work • Keeping staff involved in process/ project • Encourage consultation and listening - across all levels
Understanding compliance requirements | Risks: • Incur a non-conformance • Not controlling the job to manage hazards/ risks to requirements • Liability • Reputational impact • Audit failure • Failure to communicate a reportable accidents/incidents to external parties (e.g. to EPA, IRATA or Worksafe) • Failure to communicate accidents, incidents, hazards to internal parties. | • Develop Communication or • Training initiatives related to compliance (2 per annum) | • Continual improvement of systems • Monitoring of systems and compliance • Compliance results reviewed actively in management review meetings • Schedule internal audits of compliance management processes. • External reporting requirements identified in current system (in management review of incident form | HSE Manager and GM | Additional initiatives identified by Sept 2018 | Review Training Matrix to identify number of compliance related training or communication events.
Opportunities: • Training • Implementing system(s) • Improve knowledge/ understanding of requirements • Commitment to achieving requirements
Customer requirements and needs | Risks: • Incur liquidated damages, • defects liability, • Unable to reach practical completion • Unhappy customer | • Evaluate options to better capture/ review customer feedback • At least two client feedback per month | • Evaluate options to better capture/ review customer feedback • Improve awareness of supervisors to ask for feedback in project closure. • Establish project completion form • BD to contact clients to obtain feedback | Marketing Manager | End of 2018
Opportunities: • Repeat work with customer • Cashflow – paid on time • Customer recommendations
Cloud based systems | Risks: • Poor backup • Lack of training in use • Too many draft forms and unsubmitted documents. • Downtime • Storage capacity • Capability and restrictions • Security | • 85% of project documentation submitted on time within project • Reduce draft forms - 0% for completed / closed out projects, 30 days from date created | • Improve training • Investigate/confirm backup processes • At project close out look at forms and action / submit all draft forms or delete if form not in use for that project. • Quick over look of all forms check forms and template area of Upvise. | Operations Manager and GM | End of 2018
Opportunities: • Improved training • Knowledge sharing • Mobile access
Business risk (financial) | Risks: • Liquidity • Cashflow • Delays or not getting paid. • Incorrect invoicing (as per PO) |  | • Understand invoicing improvement opportunities • Internal understanding importance of cashflow/ invoicing • Standardise terms and conditions on invoices. • Invoicing as per PO • Cc General Manager for all invoices sent | COO and GM
Opportunities: • Process improvements to better manage cashflow • Set budgets • Invoicing asap
Project Staff awareness (quality, safety, environmental) | Risks: • QSE processes not implemented when they need to be • Not controlling the job to manage hazards/ risks to requirements • Liability • Reputational impact • Audit failure | · Develop Communication or Training initiatives related to compliance (2 per annum) | • Develop training program to improve QSE awareness and implementation • Continue project reviews and audits to identify improvement opportunities • Operations Manager and Regional Manager to provide feedback, instruction and continue monitoring | HSE Manager and GM | 2018-09-01
Opportunities: • Reputation as good provider • Improve staff knowledge and QSE understanding
Procurement | Risks: • Incorrect materials/ equipment, • Over-ordering • Project delays • Changing prices • Over budget • Difficulty sourcing specified materials | · Procurement improvement strategy to be developed | • Understanding cost/benefit of materials and equipment. • Understanding specification and contract • Improve communication and checking of current equipment with warehouse and logistics manager • Research product suitability and comparisons (including QSE implications) | Purchasing Officer and GM | 2018-12-01
Opportunities: • Increase productivity and minimise delays • Save money
Manual handling | Risks: • Injury • Down-time • Costs and insurance premiums | • Establish baseline (manual handling injuries per project hours worked) • Set target based on baseline by March 2019 | • Training • Reinforce ones’ self-responsibilities and supporting each other | HSE Manager | 2019-03-01
Opportunities: • Safer work environment • Change mentality and awareness
Communication within the business | Risks: • Loss of internet access (ADSL2) • Communication – important information not passed on or understood • Communication not consistent with internal process and protocol | • Evaluate 4G backup options • Evaluate/identify further internal meeting forums/ processes to facilitate improved communication | • Evaluate need for other internal meetings • Improve use and interaction of group emails • Evaluate 4G backup options • Recording information (detailed daily labour, project sign-off sheet) • All staff to complete general staff induction | GM | End of December 2018
Opportunities: • Consider procedure/ processes for back-up system in event of communication failure
Tenders | Risks: • Not aware of tender opportunity • Non-complying submission • Inaccurate pricing and approach • Cost of tendering • Management of RFIs | • Initiate a tender review process • Allocate tender management responsibility • Network event (attend at least one per quarter) | · • Marketing and BD resource • Increase marketing and trade shows/ conferences • Initiate a tender review process • Allocate tender management responsibility | Marketing and BD Manager | 2018-12-01
Opportunities: • Improve tender opportunity discussion (bid/ no-bid approach) • Marketing, business development and networking
Clients, including workers at client sites: Fair and transparent business relationships; competent workers, supervision and equipment to complete works in a safe, environmentally sustainable and timely fashion in accordance with agreed business terms. | Risks: • Job delivery not meeting expectations Opportunities: • Use systems to capture organizational knowledge • Mobile access to company/project information |  | • Managed through current business reporting, management and oversight processes. • No further action required (apart from continued implementation of systems).
Pty Ltd Shareholders and Directors: Profitable and sustainable business, good corporate governance, appropriate management of risk (financial, legal / compliance, OHS, environmental, reputational). | Risks: • Projects not delivered to expectations. Opportunities: • Continual improvement of systems and processes |  | · Continual improvement of systems and processes
Employees: Profitable and sustainable business, job security, fair remuneration, safe and healthy workplace, positive work environment | Risks: • Unstable workflow or other factors reduce retention rates. Opportunities: • Steady work, good communication – assist in maintaining staff. |  | · Refer to “Staff” row above
Subcontractors and their workers: Fair and transparent business relationships, payment terms, safe and healthy workplaces during project works. | Risks: • Not being able to apply same level of control to sub-contractor activities Opportunities: • Minimise use of sub-contractors where possible | · Maintain staff member on-site with contractor at all times | · Continue to ensure staff member on-site with contractor at all times | Operations Manager | Consider in project planning
Suppliers of equipment and materials: Fair and transparent business relationships, timely payment terms. | Risks: • Loss of good supplier. Opportunities: • Maintain good relationship with good suppliers. • Pro-actively review supplier performance |  | · Refer to “Procurement” and “Business Risk (financial)” row above
WorkSafe: Compliance OHS legislation; safe and healthy workplaces; compliance with workers' compensation, rehabilitation and RTW legislation. | Risks: • Non-compliance, prosecution. • Safe workplace not maintained. Opportunities: • Maintenance of safe workplace. • Industry and client recognition. | · No reportable incidents. | · Refer to “Understanding Compliance Requirements” and “Project QSE” above.
EPA: Compliance with Environmental legislation, not to pollute environment (air, water, soil, groundwater). | Risks: • Non-compliance, prosecution. • Pollution event. Opportunities: • Good environmental performance. • Industry and client recognition. | • Include awareness of pollution control requirements in training/ communication programs. • No reportable pollution events. | · Refer to “Understanding Compliance Requirements” and “Project QSE” above.
Members of the public who may be affected by our activities: They are protected from safety hazards | Risks: • Accident or injury. • Upset member of public • Damage to property or neighbouring premises. • Impact to surrounding business owners. • Don’t hold appropriate insurance • Cost of insurance premiums Opportunities: • Improved understanding and engagement processes. • Better mitigation of risks towards the public and negative impacts to . |  | • Clear communication with business owners and the public. • Communicate to staff and supervisors – the importance of reducing risk to the public.

## Sheet2
Risk, Opportunity and Objectives Register
Issue/ Expectation/ Source
Risk/ Opportunity
Related Objectives
Further Actions
Who
By When
Workflow program
Risks:
* Inconsistent work levels
* Cashflow – regular income, forecasting
* Resources unavailable to schedule works.
Opportunities:
* Marketing resource to increase consistency of workflow
* Business development
* Target areas
* Identify and engage marketing resource
* Staff training – upskill in area of business development (1% of budget)
* Develop new marketing material.
* Engage new Business Development
* Develop business development strategy
* Forecasting approach
* Staff retention (refer below)
* Microsoft project training for resource scheduling
* Review lead report in WFM in the Quarterly Management meeting
Op's Manager
New manager - July 2018
Upskilling program – commenced by September 2018
Staff
Risks:
* Morale
* Poor engagement and productivity
* Loss of key staff/ skills/ knowledge.
* Retention
* Un-safe work environment
Opportunities:
* Interesting work
* Keeping staff involved in process/ project
* Encourage consultation and listening - across all levels
* Develop staff retention strategy
* Better communication
* Staff input – encourage as part of toolbox talks and site communication
* Consider regular Supervisors and Level 3 meetings (and/or more group emails)
* Unsafe workplace – supervision, communication, systems
GM
2018-12-01
Understanding compliance requirements
Risks:
* Incur a non-conformance
* Not controlling the job to manage hazards/ risks to requirements
* Liability
* Reputational impact
* Audit failure
* Failure to communicate a reportable accidents/incidents to external parties (e.g. to EPA, IRATA or Worksafe)
* Failure to communicate accidents, incidents, hazards to internal parties.
Opportunities:
* Training
* Implementing system(s)
* Improve knowledge/ understanding of requirements
* Commitment to achieving requirements
* Develop Communication or Training initiatives related to compliance (2 per annum)
* Continual improvement of systems
* Monitoring of systems and compliance
* Compliance results reviewed actively in management review meetings
* Schedule internal audits of compliance management processes.
* External reporting requirements identified in current system (in management review of incident form)
Op's Manager and GM
Additional initiatives identified by Sept 2018
Customer requirements and needs
Risks:
* Incur liquidated damages,
* defects liability,
* Unable to reach practical completion
* Unhappy customer
Opportunities:
* Repeat work with customer
* Cashflow – paid on time
* Customer recommendations
* Evaluate options to better capture/ review customer feedback
* At least two client feedback per month
* Evaluate options to better capture/ review customer feedback
* Improve awareness of supervisors to ask for feedback in project closure.
* Establish project completion form
* BD to contact clients to obtain feedback
Marketing Manager
End of 2018
Cloud based systems
Risks:
* Poor backup
* Lack of training in use
* Too many draft forms and unsubmitted documents.
* Downtime
* Storage capacity
* Capability and restrictions
* Security
Opportunities:
* Improved training
* Knowledge sharing
* Mobile access
* 85% of project documentation submitted on time within project
* Reduce draft forms - 0% for completed / closed out projects, 30 days from date created
* Improve training
* Investigate/confirm backup processes
* At project close out look at forms and action / submit all draft forms or delete if form not in use for that project.
* Quick over look of all forms check forms and template area of Upvise.
Op's Manager and GM
End of 2018
Business risk (financial)
Risks:
* Liquidity
* Cashflow
* Delays or not getting paid.
* Incorrect invoicing (as per PO)
Opportunities:
* Process improvements to better manage cashflow
* Set budgets
* Invoicing asap
* Understand invoicing improvement opportunities
* Internal understanding importance of cashflow/ invoicing
* Standardise terms and conditions on invoices.
* Invoicing as per PO
* Cc General Manager for all invoices sent
Project Staff awareness (quality, safety, environmental)
Risks:
* QSE processes not implemented when they need to be
* Not controlling the job to manage hazards/ risks to requirements
* Liability
* Reputational impact
* Audit failure
Opportunities:
* Reputation as good provider
* Improve staff knowledge and QSE understanding
* Develop Communication or Training initiatives related to compliance (2 per annum)
* Develop training program to improve QSE awareness and implementation
* Continue project reviews and audits to identify improvement opportunities
* Operations Manager and Regional Manager to provide feedback, instruction and continue monitoring
Op's Manager and GM
2018-09-01
Procurement
Risks:
* Incorrect materials/ equipment,
* Over-ordering
* Project delays
* Changing prices
* Over budget
* Difficulty sourcing specified materials
Opportunities:
* Increase productivity and minimise delays
* Save money
* Procurement improvement strategy to be developed
* Understanding cost/benefit of materials and equipment.
* Understanding specification and contract
* Improve communication and checking of current equipment with warehouse and logistics manager
* Research product suitability and comparisons (including QSE implications)
GM
2018-12-01
Manual handling
Risks:
* Injury
* Down-time
* Costs and insurance premiums
Opportunities:
* Safer work environment
* Change mentality and awareness
* Establish baseline (manual handling injuries per project hours worked)
* Set target based on baseline by March 2019
* Training
* Reinforce ones’ self-responsibilities and supporting each other
Op's Manager
2019-03-01
Communication within the business
Risks:
* Loss of internet access (ADSL2)
* Communication – important information not passed on or understood
* Communication not consistent with internal process and protocol
Opportunities:
* Consider procedure/ processes for back-up system in event of communication failure
* Evaluate 4G backup options
* Evaluate/identify further internal meeting forums/ processes to facilitate improved communication
* Evaluate need for other internal meetings
* Improve use and interaction of group emails
* Evaluate 4G backup options
* Recording information (detailed daily labour, project sign-off sheet)
* All staff to complete general Absafe staff induction
GM
End of December 2018
Tenders
Risks:
* Not aware of tender opportunity
* Non-complying submission
* Inaccurate pricing and approach
* Cost of tendering
* Management of RFIs
Opportunities:
* Improve tender opportunity discussion (bid/ no-bid approach)
* Marketing, business development and networking
* Initiate a tender review process
* Allocate tender management responsibility
* Network event (attend at least one per quarter)
* Marketing and BD resource
* Increase marketing and trade shows/ conferences
* Initiate a tender review process
* Allocate tender management responsibility
Marketing and BD Manager
2018-12-01
Clients, including workers at client sites:
Fair and transparent business relationships; competent workers, supervision and equipment to complete works in a safe, environmentally sustainable and timely fashion in accordance with agreed business terms.
Risks:
* Job delivery not meeting expectations
Opportunities:
* Use systems to capture organizational knowledge
* Mobile access to company/project information
* Managed through current business reporting, management and oversight processes.
* No further action required (apart from continued implementation of systems).
Absafe Pty Ltd Shareholders and Directors:
Profitable and sustainable business, good corporate governance, appropriate management of risk (financial, legal / compliance, OHS, environmental, reputational).
Risks:
* Projects not delivered to expectations.
Opportunities:
* Continual improvement of systems and processes
* Continual improvement of systems and processes
Employees:
Profitable and sustainable business, job security, fair remuneration, safe and healthy workplace, positive work environment
Risks:
* Unstable workflow or other factors reduce retention rates.
Opportunities:
* Steady work, good communication – assist in maintaining staff.
* Refer to “Staff” row above
Subcontractors and their workers:
Fair and transparent business relationships, payment terms, safe and healthy workplaces during project works.
Risks:
* Not being able to apply same level of control to sub-contractor activities
Opportunities:
* Minimise use of sub-contractors where possible
* Maintain Absafe staff member on-site with contractor at all times
* Continue to ensure Absafe staff member on-site with contractor at all times
Op's Manager
Consider in project planning
Suppliers of equipment and materials:
Fair and transparent business relationships, timely payment terms.
Risks:
* Loss of good supplier.
Opportunities:
* Maintain good relationship with good suppliers.
* Pro-actively review supplier performance
* Refer to “Procurement” and “Business Risk (financial)” row above
International Rope Access Trade Association (IRATA):
Independent verification that Absafe conducts a core business activity, i.e. rope access work, to the highest possible internationally recognised standards.
Risks:
* Non-compliance with the ICOP.
* Non-compliance with audit requirements.
Opportunities:
* International recognition and acceptance
* Demonstrates Absafes commitment to safe work and safe development of the industry.
* Managed through current processes
* Continued ISO implementation assists to meet requirements.
Painting Contractor Certification Program (PCCP):
Independent verification that Absafe conducts a core business activity, industrial painting and coating works, to a recognised industry standard.
Risks:
* Non-compliance with audit requirements.
Opportunities:
* National recognition and acceptance
* Demonstrates Absafes commitment to QSE.
* Makes Absafe eligible for more tenders.
* Continued ISO implementation assists to meet requirements.
Australasian Concrete Repair Association (ACRA) and Australasian Corrosion Association (ACA)
Independent verification that Absafe conducts a core business activity, corrosion control, concrete repair, to a recognised industry standard.
Risks:
* Non-compliance with industry standards.
* Insufficient training and awareness
Opportunities:
* Demonstrates Absafes commitment to the industry.
* Provides networking and business opportunities.
* Makes Absafe more appealing to customers.
* Continue ongoing training.
* Continue conference attendance and networking events.
WorkSafe Victoria (and equivalent in other jurisdictions):
Compliance OHS legislation; safe and healthy workplaces; compliance with workers' compensation, rehabilitation and RTW legislation.
Risks:
* Non-compliance, prosecution.
* Safe workplace not maintained.
Opportunities:
* Maintenance of safe workplace.
* Industry and client recognition.
* No reportable incidents.
* Refer to “Understanding Compliance Requirements” and “Project QSE” above.
EPA Victoria (and equivalent regulators in other jurisdictions):
Compliance with Environmental legislation, not to pollute environment (air, water, soil, groundwater).
Risks:
* Non-compliance, prosecution.
* Pollution event.
Opportunities:
* Good environmental performance.
* Industry and client recognition.
* Include awareness of pollution control requirements in training/ communication programs.
* No reportable pollution events.
* Refer to “Understanding Compliance Requirements” and “Project QSE” above.
Members of the public who may be affected by Absafe's activities:
They are protected from safety hazards
Risks:
* Accident or injury.
* Upset member of public
* Damage to property or neighbouring premises.
* Impact to surrounding business owners.
* Don’t hold appropriate insurance
* Cost of insurance premiums
Opportunities:
* Improved understanding and engagement processes.
* Better mitigation of risks towards the public and negative impacts to Absafe.
* Clear communication with business owners and the public.
* Communicate to staff and supervisors – the importance of reducing risk to the public.

## Sheet3
Risk, Opportunity and Objectives Register
Issue/ Expectation/ Source
Risk/ Opportunity
Related Objectives
Further Actions
Who
By When
Workflow program
Risks:
* Inconsistent work levels
* Cashflow – regular income, forecasting
* Resources unavailable to schedule works.
Opportunities:
* Marketing resource to increase consistency of workflow
* Business development
* Target areas
* Identify and engage marketing resource
* Staff training – upskill in area of business development (1% of budget)
* Develop new marketing material.
* Engage new Business Development
* Develop business development strategy
* Forecasting approach
* Staff retention (refer below)
* Microsoft project training for resource scheduling
* Review lead report in WFM in the Quarterly Management meeting
Op's Manager
New manager - July 2018
Upskilling program – commenced by September 2018
Staff
Risks:
* Morale
* Poor engagement and productivity
* Loss of key staff/ skills/ knowledge.
* Retention
* Un-safe work environment
Opportunities:
* Interesting work
* Keeping staff involved in process/ project
* Encourage consultation and listening - across all levels
* Develop staff retention strategy
* Better communication
* Staff input – encourage as part of toolbox talks and site communication
* Consider regular Supervisors and Level 3 meetings (and/or more group emails)
* Unsafe workplace – supervision, communication, systems
GM
2018-12-01
Understanding compliance requirements
Risks:
* Incur a non-conformance
* Not controlling the job to manage hazards/ risks to requirements
* Liability
* Reputational impact
* Audit failure
* Failure to communicate a reportable accidents/incidents to external parties (e.g. to EPA, IRATA or Worksafe)
* Failure to communicate accidents, incidents, hazards to internal parties.
Opportunities:
* Training
* Implementing system(s)
* Improve knowledge/ understanding of requirements
* Commitment to achieving requirements
* Develop Communication or Training initiatives related to compliance (2 per annum)
* Continual improvement of systems
* Monitoring of systems and compliance
* Compliance results reviewed actively in management review meetings
* Schedule internal audits of compliance management processes.
* External reporting requirements identified in current system (in management review of incident form)
Op's Manager and GM
Additional initiatives identified by Sept 2018
Customer requirements and needs
Risks:
* Incur liquidated damages,
* defects liability,
* Unable to reach practical completion
* Unhappy customer
Opportunities:
* Repeat work with customer
* Cashflow – paid on time
* Customer recommendations
* Evaluate options to better capture/ review customer feedback
* At least two client feedback per month
* Evaluate options to better capture/ review customer feedback
* Improve awareness of supervisors to ask for feedback in project closure.
* Establish project completion form
* BD to contact clients to obtain feedback
Marketing Manager
End of 2018
Cloud based systems
Risks:
* Poor backup
* Lack of training in use
* Too many draft forms and unsubmitted documents.
* Downtime
* Storage capacity
* Capability and restrictions
* Security
Opportunities:
* Improved training
* Knowledge sharing
* Mobile access
* 85% of project documentation submitted on time within project
* Reduce draft forms - 0% for completed / closed out projects, 30 days from date created
* Improve training
* Investigate/confirm backup processes
* At project close out look at forms and action / submit all draft forms or delete if form not in use for that project.
* Quick over look of all forms check forms and template area of Upvise.
Op's Manager and GM
End of 2018
Business risk (financial)
Risks:
* Liquidity
* Cashflow
* Delays or not getting paid.
* Incorrect invoicing (as per PO)
Opportunities:
* Process improvements to better manage cashflow
* Set budgets
* Invoicing asap
* Understand invoicing improvement opportunities
* Internal understanding importance of cashflow/ invoicing
* Standardise terms and conditions on invoices.
* Invoicing as per PO
* Cc General Manager for all invoices sent
Project Staff awareness (quality, safety, environmental)
Risks:
* QSE processes not implemented when they need to be
* Not controlling the job to manage hazards/ risks to requirements
* Liability
* Reputational impact
* Audit failure
Opportunities:
* Reputation as good provider
* Improve staff knowledge and QSE understanding
* Develop Communication or Training initiatives related to compliance (2 per annum)
* Develop training program to improve QSE awareness and implementation
* Continue project reviews and audits to identify improvement opportunities
* Operations Manager and Regional Manager to provide feedback, instruction and continue monitoring
Op's Manager and GM
2018-09-01
Procurement
Risks:
* Incorrect materials/ equipment,
* Over-ordering
* Project delays
* Changing prices
* Over budget
* Difficulty sourcing specified materials
Opportunities:
* Increase productivity and minimise delays
* Save money
* Procurement improvement strategy to be developed
* Understanding cost/benefit of materials and equipment.
* Understanding specification and contract
* Improve communication and checking of current equipment with warehouse and logistics manager
* Research product suitability and comparisons (including QSE implications)
GM
2018-12-01
Manual handling
Risks:
* Injury
* Down-time
* Costs and insurance premiums
Opportunities:
* Safer work environment
* Change mentality and awareness
* Establish baseline (manual handling injuries per project hours worked)
* Set target based on baseline by March 2019
* Training
* Reinforce ones’ self-responsibilities and supporting each other
Op's Manager
2019-03-01
Communication within the business
Risks:
* Loss of internet access (ADSL2)
* Communication – important information not passed on or understood
* Communication not consistent with internal process and protocol
Opportunities:
* Consider procedure/ processes for back-up system in event of communication failure
* Evaluate 4G backup options
* Evaluate/identify further internal meeting forums/ processes to facilitate improved communication
* Evaluate need for other internal meetings
* Improve use and interaction of group emails
* Evaluate 4G backup options
* Recording information (detailed daily labour, project sign-off sheet)
* All staff to complete general Absafe staff induction
GM
End of December 2018
Tenders
Risks:
* Not aware of tender opportunity
* Non-complying submission
* Inaccurate pricing and approach
* Cost of tendering
* Management of RFIs
Opportunities:
* Improve tender opportunity discussion (bid/ no-bid approach)
* Marketing, business development and networking
* Initiate a tender review process
* Allocate tender management responsibility
* Network event (attend at least one per quarter)
* Marketing and BD resource
* Increase marketing and trade shows/ conferences
* Initiate a tender review process
* Allocate tender management responsibility
Marketing and BD Manager
2018-12-01
Clients, including workers at client sites:
Fair and transparent business relationships; competent workers, supervision and equipment to complete works in a safe, environmentally sustainable and timely fashion in accordance with agreed business terms.
Risks:
* Job delivery not meeting expectations
Opportunities:
* Use systems to capture organizational knowledge
* Mobile access to company/project information
* Managed through current business reporting, management and oversight processes.
* No further action required (apart from continued implementation of systems).
Absafe Pty Ltd Shareholders and Directors:
Profitable and sustainable business, good corporate governance, appropriate management of risk (financial, legal / compliance, OHS, environmental, reputational).
Risks:
* Projects not delivered to expectations.
Opportunities:
* Continual improvement of systems and processes
* Continual improvement of systems and processes
Employees:
Profitable and sustainable business, job security, fair remuneration, safe and healthy workplace, positive work environment
Risks:
* Unstable workflow or other factors reduce retention rates.
Opportunities:
* Steady work, good communication – assist in maintaining staff.
* Refer to “Staff” row above
Subcontractors and their workers:
Fair and transparent business relationships, payment terms, safe and healthy workplaces during project works.
Risks:
* Not being able to apply same level of control to sub-contractor activities
Opportunities:
* Minimise use of sub-contractors where possible
* Maintain Absafe staff member on-site with contractor at all times
* Continue to ensure Absafe staff member on-site with contractor at all times
Op's Manager
Consider in project planning
Suppliers of equipment and materials:
Fair and transparent business relationships, timely payment terms.
Risks:
* Loss of good supplier.
Opportunities:
* Maintain good relationship with good suppliers.
* Pro-actively review supplier performance
* Refer to “Procurement” and “Business Risk (financial)” row above
International Rope Access Trade Association (IRATA):
Independent verification that Absafe conducts a core business activity, i.e. rope access work, to the highest possible internationally recognised standards.
Risks:
* Non-compliance with the ICOP.
* Non-compliance with audit requirements.
Opportunities:
* International recognition and acceptance
* Demonstrates Absafes commitment to safe work and safe development of the industry.
* Managed through current processes
* Continued ISO implementation assists to meet requirements.
Painting Contractor Certification Program (PCCP):
Independent verification that Absafe conducts a core business activity, industrial painting and coating works, to a recognised industry standard.
Risks:
* Non-compliance with audit requirements.
Opportunities:
* National recognition and acceptance
* Demonstrates Absafes commitment to QSE.
* Makes Absafe eligible for more tenders.
* Continued ISO implementation assists to meet requirements.
Australasian Concrete Repair Association (ACRA) and Australasian Corrosion Association (ACA)
Independent verification that Absafe conducts a core business activity, corrosion control, concrete repair, to a recognised industry standard.
Risks:
* Non-compliance with industry standards.
* Insufficient training and awareness
Opportunities:
* Demonstrates Absafes commitment to the industry.
* Provides networking and business opportunities.
* Makes Absafe more appealing to customers.
* Continue ongoing training.
* Continue conference attendance and networking events.
WorkSafe Victoria (and equivalent in other jurisdictions):
Compliance OHS legislation; safe and healthy workplaces; compliance with workers' compensation, rehabilitation and RTW legislation.
Risks:
* Non-compliance, prosecution.
* Safe workplace not maintained.
Opportunities:
* Maintenance of safe workplace.
* Industry and client recognition.
* No reportable incidents.
* Refer to “Understanding Compliance Requirements” and “Project QSE” above.
EPA Victoria (and equivalent regulators in other jurisdictions):
Compliance with Environmental legislation, not to pollute environment (air, water, soil, groundwater).
Risks:
* Non-compliance, prosecution.
* Pollution event.
Opportunities:
* Good environmental performance.
* Industry and client recognition.
* Include awareness of pollution control requirements in training/ communication programs.
* No reportable pollution events.
* Refer to “Understanding Compliance Requirements” and “Project QSE” above.
Members of the public who may be affected by Absafe's activities:
They are protected from safety hazards
Risks:
* Accident or injury.
* Upset member of public
* Damage to property or neighbouring premises.
* Impact to surrounding business owners.
* Don’t hold appropriate insurance
* Cost of insurance premiums
Opportunities:
* Improved understanding and engagement processes.
* Better mitigation of risks towards the public and negative impacts to Absafe.
* Clear communication with business owners and the public.
* Communicate to staff and supervisors – the importance of reducing risk to the public.

## Sheet4
Risk, Opportunity and Objectives Register
Issue/ Expectation/ Source
Risk/ Opportunity
Related Objectives
Further Actions
Who
By When
Workflow program
Risks:
* Inconsistent work levels
* Cashflow – regular income, forecasting
* Resources unavailable to schedule works.
Opportunities:
* Marketing resource to increase consistency of workflow
* Business development
* Target areas
* Identify and engage marketing resource
* Staff training – upskill in area of business development (1% of budget)
* Develop new marketing material.
* Engage new Business Development
* Develop business development strategy
* Forecasting approach
* Staff retention (refer below)
* Microsoft project training for resource scheduling
* Review lead report in WFM in the Quarterly Management meeting
Op's Manager
New manager - July 2018
Upskilling program – commenced by September 2018
Staff
Risks:
* Morale
* Poor engagement and productivity
* Loss of key staff/ skills/ knowledge.
* Retention
* Un-safe work environment
Opportunities:
* Interesting work
* Keeping staff involved in process/ project
* Encourage consultation and listening - across all levels
* Develop staff retention strategy
* Better communication
* Staff input – encourage as part of toolbox talks and site communication
* Consider regular Supervisors and Level 3 meetings (and/or more group emails)
* Unsafe workplace – supervision, communication, systems
GM
2018-12-01
Understanding compliance requirements
Risks:
* Incur a non-conformance
* Not controlling the job to manage hazards/ risks to requirements
* Liability
* Reputational impact
* Audit failure
* Failure to communicate a reportable accidents/incidents to external parties (e.g. to EPA, IRATA or Worksafe)
* Failure to communicate accidents, incidents, hazards to internal parties.
Opportunities:
* Training
* Implementing system(s)
* Improve knowledge/ understanding of requirements
* Commitment to achieving requirements
* Develop Communication or Training initiatives related to compliance (2 per annum)
* Continual improvement of systems
* Monitoring of systems and compliance
* Compliance results reviewed actively in management review meetings
* Schedule internal audits of compliance management processes.
* External reporting requirements identified in current system (in management review of incident form)
Op's Manager and GM
Additional initiatives identified by Sept 2018
Customer requirements and needs
Risks:
* Incur liquidated damages,
* defects liability,
* Unable to reach practical completion
* Unhappy customer
Opportunities:
* Repeat work with customer
* Cashflow – paid on time
* Customer recommendations
* Evaluate options to better capture/ review customer feedback
* At least two client feedback per month
* Evaluate options to better capture/ review customer feedback
* Improve awareness of supervisors to ask for feedback in project closure.
* Establish project completion form
* BD to contact clients to obtain feedback
Marketing Manager
End of 2018
Cloud based systems
Risks:
* Poor backup
* Lack of training in use
* Too many draft forms and unsubmitted documents.
* Downtime
* Storage capacity
* Capability and restrictions
* Security
Opportunities:
* Improved training
* Knowledge sharing
* Mobile access
* 85% of project documentation submitted on time within project
* Reduce draft forms - 0% for completed / closed out projects, 30 days from date created
* Improve training
* Investigate/confirm backup processes
* At project close out look at forms and action / submit all draft forms or delete if form not in use for that project.
* Quick over look of all forms check forms and template area of Upvise.
Op's Manager and GM
End of 2018
Business risk (financial)
Risks:
* Liquidity
* Cashflow
* Delays or not getting paid.
* Incorrect invoicing (as per PO)
Opportunities:
* Process improvements to better manage cashflow
* Set budgets
* Invoicing asap
* Understand invoicing improvement opportunities
* Internal understanding importance of cashflow/ invoicing
* Standardise terms and conditions on invoices.
* Invoicing as per PO
* Cc General Manager for all invoices sent
Project Staff awareness (quality, safety, environmental)
Risks:
* QSE processes not implemented when they need to be
* Not controlling the job to manage hazards/ risks to requirements
* Liability
* Reputational impact
* Audit failure
Opportunities:
* Reputation as good provider
* Improve staff knowledge and QSE understanding
* Develop Communication or Training initiatives related to compliance (2 per annum)
* Develop training program to improve QSE awareness and implementation
* Continue project reviews and audits to identify improvement opportunities
* Operations Manager and Regional Manager to provide feedback, instruction and continue monitoring
Op's Manager and GM
2018-09-01
Procurement
Risks:
* Incorrect materials/ equipment,
* Over-ordering
* Project delays
* Changing prices
* Over budget
* Difficulty sourcing specified materials
Opportunities:
* Increase productivity and minimise delays
* Save money
* Procurement improvement strategy to be developed
* Understanding cost/benefit of materials and equipment.
* Understanding specification and contract
* Improve communication and checking of current equipment with warehouse and logistics manager
* Research product suitability and comparisons (including QSE implications)
GM
2018-12-01
Manual handling
Risks:
* Injury
* Down-time
* Costs and insurance premiums
Opportunities:
* Safer work environment
* Change mentality and awareness
* Establish baseline (manual handling injuries per project hours worked)
* Set target based on baseline by March 2019
* Training
* Reinforce ones’ self-responsibilities and supporting each other
Op's Manager
2019-03-01
Communication within the business
Risks:
* Loss of internet access (ADSL2)
* Communication – important information not passed on or understood
* Communication not consistent with internal process and protocol
Opportunities:
* Consider procedure/ processes for back-up system in event of communication failure
* Evaluate 4G backup options
* Evaluate/identify further internal meeting forums/ processes to facilitate improved communication
* Evaluate need for other internal meetings
* Improve use and interaction of group emails
* Evaluate 4G backup options
* Recording information (detailed daily labour, project sign-off sheet)
* All staff to complete general Absafe staff induction
GM
End of December 2018
Tenders
Risks:
* Not aware of tender opportunity
* Non-complying submission
* Inaccurate pricing and approach
* Cost of tendering
* Management of RFIs
Opportunities:
* Improve tender opportunity discussion (bid/ no-bid approach)
* Marketing, business development and networking
* Initiate a tender review process
* Allocate tender management responsibility
* Network event (attend at least one per quarter)
* Marketing and BD resource
* Increase marketing and trade shows/ conferences
* Initiate a tender review process
* Allocate tender management responsibility
Marketing and BD Manager
2018-12-01
Clients, including workers at client sites:
Fair and transparent business relationships; competent workers, supervision and equipment to complete works in a safe, environmentally sustainable and timely fashion in accordance with agreed business terms.
Risks:
* Job delivery not meeting expectations
Opportunities:
* Use systems to capture organizational knowledge
* Mobile access to company/project information
* Managed through current business reporting, management and oversight processes.
* No further action required (apart from continued implementation of systems).
Absafe Pty Ltd Shareholders and Directors:
Profitable and sustainable business, good corporate governance, appropriate management of risk (financial, legal / compliance, OHS, environmental, reputational).
Risks:
* Projects not delivered to expectations.
Opportunities:
* Continual improvement of systems and processes
* Continual improvement of systems and processes
Employees:
Profitable and sustainable business, job security, fair remuneration, safe and healthy workplace, positive work environment
Risks:
* Unstable workflow or other factors reduce retention rates.
Opportunities:
* Steady work, good communication – assist in maintaining staff.
* Refer to “Staff” row above
Subcontractors and their workers:
Fair and transparent business relationships, payment terms, safe and healthy workplaces during project works.
Risks:
* Not being able to apply same level of control to sub-contractor activities
Opportunities:
* Minimise use of sub-contractors where possible
* Maintain Absafe staff member on-site with contractor at all times
* Continue to ensure Absafe staff member on-site with contractor at all times
Op's Manager
Consider in project planning
Suppliers of equipment and materials:
Fair and transparent business relationships, timely payment terms.
Risks:
* Loss of good supplier.
Opportunities:
* Maintain good relationship with good suppliers.
* Pro-actively review supplier performance
* Refer to “Procurement” and “Business Risk (financial)” row above
International Rope Access Trade Association (IRATA):
Independent verification that Absafe conducts a core business activity, i.e. rope access work, to the highest possible internationally recognised standards.
Risks:
* Non-compliance with the ICOP.
* Non-compliance with audit requirements.
Opportunities:
* International recognition and acceptance
* Demonstrates Absafes commitment to safe work and safe development of the industry.
* Managed through current processes
* Continued ISO implementation assists to meet requirements.
Painting Contractor Certification Program (PCCP):
Independent verification that Absafe conducts a core business activity, industrial painting and coating works, to a recognised industry standard.
Risks:
* Non-compliance with audit requirements.
Opportunities:
* National recognition and acceptance
* Demonstrates Absafes commitment to QSE.
* Makes Absafe eligible for more tenders.
* Continued ISO implementation assists to meet requirements.
Australasian Concrete Repair Association (ACRA) and Australasian Corrosion Association (ACA)
Independent verification that Absafe conducts a core business activity, corrosion control, concrete repair, to a recognised industry standard.
Risks:
* Non-compliance with industry standards.
* Insufficient training and awareness
Opportunities:
* Demonstrates Absafes commitment to the industry.
* Provides networking and business opportunities.
* Makes Absafe more appealing to customers.
* Continue ongoing training.
* Continue conference attendance and networking events.
WorkSafe Victoria (and equivalent in other jurisdictions):
Compliance OHS legislation; safe and healthy workplaces; compliance with workers' compensation, rehabilitation and RTW legislation.
Risks:
* Non-compliance, prosecution.
* Safe workplace not maintained.
Opportunities:
* Maintenance of safe workplace.
* Industry and client recognition.
* No reportable incidents.
* Refer to “Understanding Compliance Requirements” and “Project QSE” above.
EPA Victoria (and equivalent regulators in other jurisdictions):
Compliance with Environmental legislation, not to pollute environment (air, water, soil, groundwater).
Risks:
* Non-compliance, prosecution.
* Pollution event.
Opportunities:
* Good environmental performance.
* Industry and client recognition.
* Include awareness of pollution control requirements in training/ communication programs.
* No reportable pollution events.
* Refer to “Understanding Compliance Requirements” and “Project QSE” above.
Members of the public who may be affected by Absafe's activities:
They are protected from safety hazards
Risks:
* Accident or injury.
* Upset member of public
* Damage to property or neighbouring premises.
* Impact to surrounding business owners.
* Don’t hold appropriate insurance
* Cost of insurance premiums
Opportunities:
* Improved understanding and engagement processes.
* Better mitigation of risks towards the public and negative impacts to Absafe.
* Clear communication with business owners and the public.
* Communicate to staff and supervisors – the importance of reducing risk to the public.

## Sheet5
Risk, Opportunity and Objectives Register
Issue/ Expectation/ Source
Risk/ Opportunity
Related Objectives
Further Actions
Who
By When
Workflow program
Risks:
* Inconsistent work levels
* Cashflow – regular income, forecasting
* Resources unavailable to schedule works.
Opportunities:
* Marketing resource to increase consistency of workflow
* Business development
* Target areas
* Identify and engage marketing resource
* Staff training – upskill in area of business development | (1% of budget)
* Develop new marketing material.
* Engage new Business Development
* Develop business development strategy
* Forecasting approach
* Staff retention (refer below)
* Microsoft project training for resource scheduling
* Review lead report in WFM in the Quarterly Management mee | ting
Op's Manager
New manager - July 2018
Upskilling program – commenced by September 2018
Staff
Risks:
* Morale
* Poor engagement and productivity
* Loss of key staff/ skills/ knowledge.
* Retention
* Un-safe work environment
Opportunities:
* Interesting work
* Keeping staff involved in process/ project
* Encourage consultation and listening - across all levels
* Develop staff retention strategy
* Better communication
* Staff input – encourage as part of toolbox talks and site | communication
* Consider regular Supervisors and Level 3 meetings (and/or | more group emails)
* Unsafe workplace – supervision, communication, systems
GM
2018-12-01
Understanding compliance requirements
Risks:
* Incur a non-conformance
* Not controlling the job to manage hazards/ risks to requi | rements
* Liability
* Reputational impact
* Audit failure
* Failure to communicate a reportable accidents/incidents t | o external parties (e.g. to EPA, IRATA or Worksafe)
* Failure to communicate accidents, incidents, hazards to i | nternal parties.
Opportunities:
* Training
* Implementing system(s)
* Improve knowledge/ understanding of requirements
* Commitment to achieving requirements
* Develop Communication or Training initiatives related to | compliance (2 per annum)
* Continual improvement of systems
* Monitoring of systems and compliance
* Compliance results reviewed actively in management review | meetings
* Schedule internal audits of compliance management process | es.
* External reporting requirements identified in current sys | tem (in management review of incident form)
Op's Manager and GM
Additional initiatives identified by Sept 2018
Customer requirements and needs
Risks:
* Incur liquidated damages,
* defects liability,
* Unable to reach practical completion
* Unhappy customer
Opportunities:
* Repeat work with customer
* Cashflow – paid on time
* Customer recommendations
* Evaluate options to better capture/ review customer feedb | ack
* At least two client feedback per month
* Evaluate options to better capture/ review customer feedb | ack
* Improve awareness of supervisors to ask for feedback in p | roject closure.
* Establish project completion form
* BD to contact clients to obtain feedback
Marketing Manager
End of 2018
Cloud based systems
Risks:
* Poor backup
* Lack of training in use
* Too many draft forms and unsubmitted documents.
* Downtime
* Storage capacity
* Capability and restrictions
* Security
Opportunities:
* Improved training
* Knowledge sharing
* Mobile access
* 85% of project documentation submitted on time within pro | ject
* Reduce draft forms - 0% for completed / closed out proje | cts, 30 days from date created
* Improve training
* Investigate/confirm backup processes
* At project close out look at forms and action / submit al | l draft forms or delete if form not in use for that project.
* Quick over look of all forms check forms and template are | a of Upvise.
Op's Manager and GM
End of 2018
Business risk (financial)
Risks:
* Liquidity
* Cashflow
* Delays or not getting paid.
* Incorrect invoicing (as per PO)
Opportunities:
* Process improvements to better manage cashflow
* Set budgets
* Invoicing asap
* Understand invoicing improvement opportunities
* Internal understanding importance of cashflow/ invoicing
* Standardise terms and conditions on invoices.
* Invoicing as per PO
* Cc General Manager for all invoices sent
Project Staff awareness (quality, safety, environmental)
Risks:
* QSE processes not implemented when they need to be
* Not controlling the job to manage hazards/ risks to requi | rements
* Liability
* Reputational impact
* Audit failure
Opportunities:
* Reputation as good provider
* Improve staff knowledge and QSE understanding
* Develop Communication or Training initiatives related to | compliance (2 per annum)
* Develop training program to improve QSE awareness and imp | lementation
* Continue project reviews and audits to identify improveme | nt opportunities
* Operations Manager and Regional Manager to provide feedba | ck, instruction and continue monitoring
Op's Manager and GM
2018-09-01
Procurement
Risks:
* Incorrect materials/ equipment,
* Over-ordering
* Project delays
* Changing prices
* Over budget
* Difficulty sourcing specified materials
Opportunities:
* Increase productivity and minimise delays
* Save money
* Procurement improvement strategy to be developed
* Understanding cost/benefit of materials and equipment.
* Understanding specification and contract
* Improve communication and checking of current equipment w | ith warehouse and logistics manager
* Research product suitability and comparisons (including Q | SE implications)
GM
2018-12-01
Manual handling
Risks:
* Injury
* Down-time
* Costs and insurance premiums
Opportunities:
* Safer work environment
* Change mentality and awareness
* Establish baseline (manual handling injuries per project | hours worked)
* Set target based on baseline by March 2019
* Training
* Reinforce ones’ self-responsibilities and supporting each | other
Op's Manager
2019-03-01
Communication within the business
Risks:
* Loss of internet access (ADSL2)
* Communication – important information not passed on or un | derstood
* Communication not consistent with internal process and pr | otocol
Opportunities:
* Consider procedure/ processes for back-up system in event | of communication failure
* Evaluate 4G backup options
* Evaluate/identify further internal meeting forums/ proces | ses to facilitate improved communication
* Evaluate need for other internal meetings
* Improve use and interaction of group emails
* Evaluate 4G backup options
* Recording information (detailed daily labour, project sig | n-off sheet)
* All staff to complete general Absafe staff induction
GM
End of December 2018
Tenders
Risks:
* Not aware of tender opportunity
* Non-complying submission
* Inaccurate pricing and approach
* Cost of tendering
* Management of RFIs
Opportunities:
* Improve tender opportunity discussion (bid/ no-bid approa | ch)
* Marketing, business development and networking
* Initiate a tender review process
* Allocate tender management responsibility
* Network event (attend at least one per quarter)
* Marketing and BD resource
* Increase marketing and trade shows/ conferences
* Initiate a tender review process
* Allocate tender management responsibility
Marketing and BD Manager
2018-12-01
Clients, including workers at client sites:
Fair and transparent business relationships; competent work | ers, supervision and equipment to complete works in a safe, environmentally sustainable and timely fashion in accordance with agreed business terms.
Risks:
* Job delivery not meeting expectations
Opportunities:
* Use systems to capture organizational knowledge
* Mobile access to company/project information
* Managed through current business reporting, management an | d oversight processes.
* No further action required (apart from continued implemen | tation of systems).
Absafe Pty Ltd Shareholders and Directors:
Profitable and sustainable business, good corporate governa | nce, appropriate management of risk (financial, legal / compliance, OHS, environmental, reputational).
Risks:
* Projects not delivered to expectations.
Opportunities:
* Continual improvement of systems and processes
* Continual improvement of systems and processes
Employees:
Profitable and sustainable business, job security, fair rem | uneration, safe and healthy workplace, positive work environment
Risks:
* Unstable workflow or other factors reduce retention rates | .
Opportunities:
* Steady work, good communication – assist in maintaining s | taff.
* Refer to “Staff” row above
Subcontractors and their workers:
Fair and transparent business relationships, payment terms, | safe and healthy workplaces during project works.
Risks:
* Not being able to apply same level of control to sub-cont | ractor activities
Opportunities:
* Minimise use of sub-contractors where possible
* Maintain Absafe staff member on-site with contractor at a | ll times
* Continue to ensure Absafe staff member on-site with contr | actor at all times
Op's Manager
Consider in project planning
Suppliers of equipment and materials:
Fair and transparent business relationships, timely payment | terms.
Risks:
* Loss of good supplier.
Opportunities:
* Maintain good relationship with good suppliers.
* Pro-actively review supplier performance
* Refer to “Procurement” and “Business Risk (financial)” ro | w above
International Rope Access Trade Association (IRATA):
Independent verification that Absafe conducts a core busine | ss activity, i.e. rope access work, to the highest possible internationally recognised standards.
Risks:
* Non-compliance with the ICOP.
* Non-compliance with audit requirements.
Opportunities:
* International recognition and acceptance
* Demonstrates Absafes commitment to safe work and safe dev | elopment of the industry.
* Managed through current processes
* Continued ISO implementation assists to meet requirements | .
Painting Contractor Certification Program (PCCP):
Independent verification that Absafe conducts a core busine | ss activity, industrial painting and coating works, to a recognised industry standard.
Risks:
* Non-compliance with audit requirements.
Opportunities:
* National recognition and acceptance
* Demonstrates Absafes commitment to QSE.
* Makes Absafe eligible for more tenders.
* Continued ISO implementation assists to meet requirements | .
Australasian Concrete Repair Association (ACRA) and Austral | asian Corrosion Association (ACA)
Independent verification that Absafe conducts a core busine | ss activity, corrosion control, concrete repair, to a recognised industry standard.
Risks:
* Non-compliance with industry standards.
* Insufficient training and awareness
Opportunities:
* Demonstrates Absafes commitment to the industry.
* Provides networking and business opportunities.
* Makes Absafe more appealing to customers.
* Continue ongoing training.
* Continue conference attendance and networking events.
WorkSafe Victoria (and equivalent in other jurisdictions):
Compliance OHS legislation; safe and healthy workplaces; co | mpliance with workers' compensation, rehabilitation and RTW legislation.
Risks:
* Non-compliance, prosecution.
* Safe workplace not maintained.
Opportunities:
* Maintenance of safe workplace.
* Industry and client recognition.
* No reportable incidents.
* Refer to “Understanding Compliance Requirements” and “Pro | ject QSE” above.
EPA Victoria (and equivalent regulators in other jurisdicti | ons):
Compliance with Environmental legislation, not to pollute e | nvironment (air, water, soil, groundwater).
Risks:
* Non-compliance, prosecution.
* Pollution event.
Opportunities:
* Good environmental performance.
* Industry and client recognition.
* Include awareness of pollution control requirements in tr | aining/ communication programs.
* No reportable pollution events.
* Refer to “Understanding Compliance Requirements” and “Pro | ject QSE” above.
Members of the public who may be affected by Absafe's activ | ities:
They are protected from safety hazards
Risks:
* Accident or injury.
* Upset member of public
* Damage to property or neighbouring premises.
* Impact to surrounding business owners.
* Don’t hold appropriate insurance
* Cost of insurance premiums
Opportunities:
* Improved understanding and engagement processes.
* Better mitigation of risks towards the public and negativ | e impacts to Absafe.
* Clear communication with business owners and the public.
* Communicate to staff and supervisors – the importance of | reducing risk to the public.

## Sheet6
Risk, Opportunity and Objectives Register
Issue/ Expectation/ Source
Risk/ Opportunity
Related Objectives
Further Actions
Who
By When
Workflow program
Risks:
* Inconsistent work levels
* Cashflow Ð regular income, forecasting
* Resources unavailable to schedule works.
Opportunities:
* Marketing resource to increase consistency of workflow
* Business development
* Target areas
* Identify and engage marketing resource
* Staff training Ð upskill in area of business development (1% of budget)
* Develop new marketing material.
* Engage new Business Development
* Develop business development strategy
* Forecasting approach
* Staff retention (refer below)
* Microsoft project training for resource scheduling
* Review lead report in WFM in the Quarterly Management meeting
Op's Manager
New manager - July 2018
Upskilling program Ð commenced by September 2018
Staff
Risks:
* Morale
* Poor engagement and productivity
* Loss of key staff/ skills/ knowledge.
* Retention
* Un-safe work environment
Opportunities:
* Interesting work
* Keeping staff involved in process/ project
* Encourage consultation and listening - across all levels
* Develop staff retention strategy
* Better communication
* Staff input Ð encourage as part of toolbox talks and site communication
* Consider regular Supervisors and Level 3 meetings (and/or more group emails)
* Unsafe workplace Ð supervision, communication, systems
GM
2018-12-01
Understanding compliance requirements
Risks:
* Incur a non-conformance
* Not controlling the job to manage hazards/ risks to requirements
* Liability
* Reputational impact
* Audit failure
* Failure to communicate a reportable accidents/incidents to external parties (e.g. to EPA, IRATA or Worksafe)
* Failure to communicate accidents, incidents, hazards to internal parties.
Opportunities:
* Training
* Implementing system(s)
* Improve knowledge/ understanding of requirements
* Commitment to achieving requirements
* Develop Communication or Training initiatives related to compliance (2 per annum)
* Continual improvement of systems
* Monitoring of systems and compliance
* Compliance results reviewed actively in management review meetings
* Schedule internal audits of compliance management processes.
* External reporting requirements identified in current system (in management review of incident form)
Op's Manager and GM
Additional initiatives identified by Sept 2018
Customer requirements and needs
Risks:
* Incur liquidated damages,
* defects liability,
* Unable to reach practical completion
* Unhappy customer
Opportunities:
* Repeat work with customer
* Cashflow Ð paid on time
* Customer recommendations
* Evaluate options to better capture/ review customer feedback
* At least two client feedback per month
* Evaluate options to better capture/ review customer feedback
* Improve awareness of supervisors to ask for feedback in project closure.
* Establish project completion form
* BD to contact clients to obtain feedback
Marketing Manager
End of 2018
Cloud based systems
Risks:
* Poor backup
* Lack of training in use
* Too many draft forms and unsubmitted documents.
* Downtime
* Storage capacity
* Capability and restrictions
* Security
Opportunities:
* Improved training
* Knowledge sharing
* Mobile access
* 85% of project documentation submitted on time within project
* Reduce draft forms - 0% for completed / closed out projects, 30 days from date created
* Improve training
* Investigate/confirm backup processes
* At project close out look at forms and action / submit all draft forms or delete if form not in use for that project.
* Quick over look of all forms check forms and template area of Upvise.
Op's Manager and GM
End of 2018
Business risk (financial)
Risks:
* Liquidity
* Cashflow
* Delays or not getting paid.
* Incorrect invoicing (as per PO)
Opportunities:
* Process improvements to better manage cashflow
* Set budgets
* Invoicing asap
* Understand invoicing improvement opportunities
* Internal understanding importance of cashflow/ invoicing
* Standardise terms and conditions on invoices.
* Invoicing as per PO
* Cc General Manager for all invoices sent
Project Staff awareness (quality, safety, environmental)
Risks:
* QSE processes not implemented when they need to be
* Not controlling the job to manage hazards/ risks to requirements
* Liability
* Reputational impact
* Audit failure
Opportunities:
* Reputation as good provider
* Improve staff knowledge and QSE understanding
* Develop Communication or Training initiatives related to compliance (2 per annum)
* Develop training program to improve QSE awareness and implementation
* Continue project reviews and audits to identify improvement opportunities
* Operations Manager and Regional Manager to provide feedback, instruction and continue monitoring
Op's Manager and GM
2018-09-01
Procurement
Risks:
* Incorrect materials/ equipment,
* Over-ordering
* Project delays
* Changing prices
* Over budget
* Difficulty sourcing specified materials
Opportunities:
* Increase productivity and minimise delays
* Save money
* Procurement improvement strategy to be developed
* Understanding cost/benefit of materials and equipment.
* Understanding specification and contract
* Improve communication and checking of current equipment with warehouse and logistics manager
* Research product suitability and comparisons (including QSE implications)
GM
2018-12-01
Manual handling
Risks:
* Injury
* Down-time
* Costs and insurance premiums
Opportunities:
* Safer work environment
* Change mentality and awareness
* Establish baseline (manual handling injuries per project hours worked)
* Set target based on baseline by March 2019
* Training
* Reinforce onesÕ self-responsibilities and supporting each other
Op's Manager
2019-03-01
Communication within the business
Risks:
* Loss of internet access (ADSL2)
* Communication Ð important information not passed on or understood
* Communication not consistent with internal process and protocol
Opportunities:
* Consider procedure/ processes for back-up system in event of communication failure
* Evaluate 4G backup options
* Evaluate/identify further internal meeting forums/ processes to facilitate improved communication
* Evaluate need for other internal meetings
* Improve use and interaction of group emails
* Evaluate 4G backup options
* Recording information (detailed daily labour, project sign-off sheet)
* All staff to complete general Absafe staff induction
GM
End of December 2018
Tenders
Risks:
* Not aware of tender opportunity
* Non-complying submission
* Inaccurate pricing and approach
* Cost of tendering
* Management of RFIs
Opportunities:
* Improve tender opportunity discussion (bid/ no-bid approach)
* Marketing, business development and networking
* Initiate a tender review process
* Allocate tender management responsibility
* Network event (attend at least one per quarter)
* Marketing and BD resource
* Increase marketing and trade shows/ conferences
* Initiate a tender review process
* Allocate tender management responsibility
Marketing and BD Manager
2018-12-01
Clients, including workers at client sites:
Fair and transparent business relationships; competent workers, supervision and equipment to complete works in a safe, environmentally sustainable and timely fashion in accordance with agreed business terms.
Risks:
* Job delivery not meeting expectations
Opportunities:
* Use systems to capture organizational knowledge
* Mobile access to company/project information
* Managed through current business reporting, management and oversight processes.
* No further action required (apart from continued implementation of systems).
Absafe Pty Ltd Shareholders and Directors:
Profitable and sustainable business, good corporate governance, appropriate management of risk (financial, legal / compliance, OHS, environmental, reputational).
Risks:
* Projects not delivered to expectations.
Opportunities:
* Continual improvement of systems and processes
* Continual improvement of systems and processes
Employees:
Profitable and sustainable business, job security, fair remuneration, safe and healthy workplace, positive work environment
Risks:
* Unstable workflow or other factors reduce retention rates.
Opportunities:
* Steady work, good communication Ð assist in maintaining staff.
* Refer to ÒStaffÓ row above
Subcontractors and their workers:
Fair and transparent business relationships, payment terms, safe and healthy workplaces during project works.
Risks:
* Not being able to apply same level of control to sub-contractor activities
Opportunities:
* Minimise use of sub-contractors where possible
* Maintain Absafe staff member on-site with contractor at all times
* Continue to ensure Absafe staff member on-site with contractor at all times
Op's Manager
Consider in project planning
Suppliers of equipment and materials:
Fair and transparent business relationships, timely payment terms.
Risks:
* Loss of good supplier.
Opportunities:
* Maintain good relationship with good suppliers.
* Pro-actively review supplier performance
* Refer to ÒProcurementÓ and ÒBusiness Risk (financial)Ó row above
International Rope Access Trade Association (IRATA):
Independent verification that Absafe conducts a core business activity, i.e. rope access work, to the highest possible internationally recognised standards.
Risks:
* Non-compliance with the ICOP.
* Non-compliance with audit requirements.
Opportunities:
* International recognition and acceptance
* Demonstrates Absafes commitment to safe work and safe development of the industry.
* Managed through current processes
* Continued ISO implementation assists to meet requirements.
Painting Contractor Certification Program (PCCP):
Independent verification that Absafe conducts a core business activity, industrial painting and coating works, to a recognised industry standard.
Risks:
* Non-compliance with audit requirements.
Opportunities:
* National recognition and acceptance
* Demonstrates Absafes commitment to QSE.
* Makes Absafe eligible for more tenders.
* Continued ISO implementation assists to meet requirements.
Australasian Concrete RepairÊAssociation (ACRA) and Australasian Corrosion Association (ACA)
Independent verification that Absafe conducts a core business activity, corrosion control, concrete repair, to a recognised industry standard.
Risks:
* Non-compliance with industry standards.
* Insufficient training and awareness
Opportunities:
* Demonstrates Absafes commitment to the industry.
* Provides networking and business opportunities.
* Makes Absafe more appealing to customers.
* Continue ongoing training.
* Continue conference attendance and networking events.
WorkSafe Victoria (and equivalent in other jurisdictions):
Compliance OHS legislation; safe and healthy workplaces; compliance with workers' compensation, rehabilitation and RTW legislation.
Risks:
* Non-compliance, prosecution.
* Safe workplace not maintained.
Opportunities:
* Maintenance of safe workplace.
* Industry and client recognition.
* No reportable incidents.
* Refer to ÒUnderstanding Compliance RequirementsÓ and ÒProject QSEÓ above.
EPA Victoria (and equivalent regulators in other jurisdictions):
Compliance with Environmental legislation, not to pollute environment (air, water, soil, groundwater).
Risks:
* Non-compliance, prosecution.
* Pollution event.
Opportunities:
* Good environmental performance.
* Industry and client recognition.
* Include awareness of pollution control requirements in training/ communication programs.
* No reportable pollution events.
* Refer to ÒUnderstanding Compliance RequirementsÓ and ÒProject QSEÓ above.
Members of the public who may be affected by Absafe's activities:
They are protected from safety hazards
Risks:
* Accident or injury.
* Upset member of public
* Damage to property or neighbouring premises.
* Impact to surrounding business owners.
* DonÕt hold appropriate insurance
* Cost of insurance premiums
Opportunities:
* Improved understanding and engagement processes.
* Better mitigation of risks towards the public and negative impacts to Absafe.
* Clear communication with business owners and the public.
* Communicate to staff and supervisors Ð the importance of reducing risk to the public.

## Sheet7
Risk, | Opportunity | and | Objectives | Register
Issue/ | Expectation/ | Source
Risk/ | Opportunity
Related | Objectives
Further | Actions
Who
By | When
Workflow | program
Risks:
* | Inconsistent | work | levels
* | Cashflow | – | regular | income, | forecasting
* | Resources | unavailable | to | schedule | works.
Opportunities:
* | Marketing | resource | to | increase | consistency | of | workflow
* | Business | development
* | Target | areas
* | Identify | and | engage | marketing | resource
* | Staff | training | – | upskill | in | area | of | business | development | (1% | of | budget)
* | Develop | new | marketing | material.
* | Engage | new | Business | Development
* | Develop | business | development | strategy
* | Forecasting | approach
* | Staff | retention | (refer | below)
* | Microsoft | project | training | for | resource | scheduling
* | Review | lead | report | in | WFM | in | the | Quarterly | Management | meeting
Op's | Manager
New | manager | - | July | 2018
Upskilling | program | – | commenced | by | September | 2018
Staff
Risks:
* | Morale
* | Poor | engagement | and | productivity
* | Loss | of | key | staff/ | skills/ | knowledge.
* | Retention
* | Un-safe | work | environment
Opportunities:
* | Interesting | work
* | Keeping | staff | involved | in | process/ | project
* | Encourage | consultation | and | listening | - | across | all | levels
* | Develop | staff | retention | strategy
* | Better | communication
* | Staff | input | – | encourage | as | part | of | toolbox | talks | and | site | communication
* | Consider | regular | Supervisors | and | Level | 3 | meetings | (and/or | more | group | emails)
* | Unsafe | workplace | – | supervision, | communication, | systems
GM
December | 2018
Understanding | compliance | requirements
Risks:
* | Incur | a | non-conformance
* | Not | controlling | the | job | to | manage | hazards/ | risks | to | requirements
* | Liability
* | Reputational | impact
* | Audit | failure
* | Failure | to | communicate | a | reportable | accidents/incidents | to | external | parties | (e.g. | to | EPA, | IRATA | or | Worksafe)
* | Failure | to | communicate | accidents, | incidents, | hazards | to | internal | parties.
Opportunities:
* | Training
* | Implementing | system(s)
* | Improve | knowledge/ | understanding | of | requirements
* | Commitment | to | achieving | requirements
* | Develop | Communication | or | Training | initiatives | related | to | compliance | (2 | per | annum)
* | Continual | improvement | of | systems
* | Monitoring | of | systems | and | compliance
* | Compliance | results | reviewed | actively | in | management | review | meetings
* | Schedule | internal | audits | of | compliance | management | processes.
* | External | reporting | requirements | identified | in | current | system | (in | management | review | of | incident | form)
Op's | Manager | and | GM
Additional | initiatives | identified | by | Sept | 2018
Customer | requirements | and | needs
Risks:
* | Incur | liquidated | damages,
* | defects | liability,
* | Unable | to | reach | practical | completion
* | Unhappy | customer
Opportunities:
* | Repeat | work | with | customer
* | Cashflow | – | paid | on | time
* | Customer | recommendations
* | Evaluate | options | to | better | capture/ | review | customer | feedback
* | At | least | two | client | feedback | per | month
* | Evaluate | options | to | better | capture/ | review | customer | feedback
* | Improve | awareness | of | supervisors | to | ask | for | feedback | in | project | closure.
* | Establish | project | completion | form
* | BD | to | contact | clients | to | obtain | feedback
Marketing | Manager
End | of | 2018
Cloud | based | systems
Risks:
* | Poor | backup
* | Lack | of | training | in | use
* | Too | many | draft | forms | and | unsubmitted | documents.
* | Downtime
* | Storage | capacity
* | Capability | and | restrictions
* | Security
Opportunities:
* | Improved | training
* | Knowledge | sharing
* | Mobile | access
* | 85% | of | project | documentation | submitted | on | time | within | project
* | Reduce | draft | forms | - | 0% | for | completed |  | / | closed | out | projects, | 30 | days | from | date | created
* | Improve | training
* | Investigate/confirm | backup | processes
* | At | project | close | out | look | at | forms | and | action | / | submit | all | draft | forms | or | delete | if | form | not | in | use | for | that | project.
* | Quick | over | look | of | all | forms | check | forms | and | template | area | of | Upvise.
Op's | Manager | and | GM
End | of | 2018
Business | risk | (financial)
Risks:
* | Liquidity
* | Cashflow
* | Delays | or | not | getting | paid.
* | Incorrect | invoicing | (as | per | PO)
Opportunities:
* | Process | improvements | to | better | manage | cashflow
* | Set | budgets
* | Invoicing | asap
* | Understand | invoicing | improvement | opportunities
* | Internal | understanding | importance | of | cashflow/ | invoicing
* | Standardise | terms | and | conditions | on | invoices.
* | Invoicing | as | per | PO
* | Cc | General | Manager | for | all | invoices | sent
Project | Staff | awareness | (quality, | safety, | environmental)
Risks:
* | QSE | processes | not | implemented | when | they | need | to | be
* | Not | controlling | the | job | to | manage | hazards/ | risks | to | requirements
* | Liability
* | Reputational | impact
* | Audit | failure
Opportunities:
* | Reputation | as | good | provider
* | Improve | staff | knowledge | and | QSE | understanding
* | Develop | Communication | or | Training | initiatives | related | to | compliance | (2 | per | annum)
* | Develop | training | program | to | improve | QSE | awareness | and | implementation
* | Continue | project | reviews | and | audits | to | identify | improvement | opportunities
* | Operations | Manager | and | Regional | Manager | to | provide | feedback, | instruction | and | continue | monitoring
Op's | Manager | and | GM
Sept | 2018
Procurement
Risks:
* | Incorrect | materials/ | equipment,
* | Over-ordering
* | Project | delays
* | Changing | prices
* | Over | budget
* | Difficulty | sourcing | specified | materials
Opportunities:
* | Increase | productivity | and | minimise | delays
* | Save | money
* | Procurement | improvement | strategy | to | be | developed
* | Understanding | cost/benefit | of | materials | and | equipment.
* | Understanding | specification | and | contract
* | Improve | communication | and | checking | of | current | equipment | with | warehouse | and | logistics | manager
* | Research | product | suitability | and | comparisons | (including | QSE | implications)
GM
December | 2018
Manual | handling
Risks:
* | Injury
* | Down-time
* | Costs | and | insurance | premiums
Opportunities:
* | Safer | work | environment
* | Change | mentality | and | awareness
* | Establish | baseline | (manual | handling | injuries | per | project | hours | worked)
* | Set | target | based | on | baseline | by | March | 2019
* | Training
* | Reinforce | ones’ | self-responsibilities | and | supporting | each | other
Op's | Manager
March | 2019
Communication | within | the | business
Risks:
* | Loss | of | internet | access | (ADSL2)
* | Communication | – | important | information | not | passed | on | or | understood
* | Communication | not | consistent | with | internal | process | and | protocol
Opportunities:
* | Consider | procedure/ | processes | for | back-up | system | in | event | of | communication | failure
* | Evaluate | 4G | backup | options
* | Evaluate/identify | further | internal | meeting | forums/ | processes | to | facilitate | improved | communication
* | Evaluate | need | for | other | internal | meetings
* | Improve | use | and | interaction | of | group | emails
* | Evaluate | 4G | backup | options
* | Recording | information | (detailed | daily | labour, | project | sign-off | sheet)
* | All | staff | to | complete | general | Absafe | staff | induction
GM
End | of | December | 2018
Tenders
Risks:
* | Not | aware | of | tender | opportunity
* | Non-complying | submission
* | Inaccurate | pricing | and | approach
* | Cost | of | tendering
* | Management | of | RFIs
Opportunities:
* | Improve | tender | opportunity | discussion | (bid/ | no-bid | approach)
* | Marketing, | business | development | and | networking
* | Initiate | a | tender | review | process
* | Allocate | tender | management | responsibility
* | Network | event | (attend | at | least | one | per | quarter)
* | Marketing | and | BD | resource
* | Increase | marketing | and | trade | shows/ | conferences
* | Initiate | a | tender | review | process
* | Allocate | tender | management | responsibility
Marketing | and | BD | Manager
December | 2018
Clients, | including | workers | at | client | sites:
Fair | and | transparent | business | relationships; | competent | workers, | supervision | and | equipment | to | complete | works | in | a | safe, | environmentally | sustainable | and | timely | fashion | in | accordance | with | agreed | business | terms.
Risks:
* | Job | delivery | not | meeting | expectations
Opportunities:
* | Use | systems | to | capture | organizational | knowledge
* | Mobile | access | to | company/project | information
* | Managed | through | current | business | reporting, | management | and | oversight | processes.
* | No | further | action | required | (apart | from | continued | implementation | of | systems).
Absafe | Pty | Ltd | Shareholders | and | Directors:
Profitable | and | sustainable | business, | good | corporate | governance, | appropriate | management | of | risk | (financial, | legal | / | compliance, | OHS, | environmental, | reputational).
Risks:
* | Projects | not | delivered | to | expectations.
Opportunities:
* | Continual | improvement | of | systems | and | processes
* | Continual | improvement | of | systems | and | processes
Employees:
Profitable | and | sustainable | business, | job | security, | fair | remuneration, | safe | and | healthy | workplace, | positive | work | environment
Risks:
* | Unstable | workflow | or | other | factors | reduce | retention | rates.
Opportunities:
* | Steady | work, | good | communication | – | assist | in | maintaining | staff.
* | Refer | to | “Staff” | row | above
Subcontractors | and | their | workers:
Fair | and | transparent | business | relationships, | payment | terms, | safe | and | healthy | workplaces | during | project | works.
Risks:
* | Not | being | able | to | apply | same | level | of | control | to | sub-contractor | activities
Opportunities:
* | Minimise | use | of | sub-contractors | where | possible
* | Maintain | Absafe | staff | member | on-site | with | contractor | at | all | times
* | Continue | to | ensure | Absafe | staff | member | on-site | with | contractor | at | all | times
Op's | Manager
Consider | in | project | planning
Suppliers | of | equipment | and | materials:
Fair | and | transparent | business | relationships, | timely | payment | terms.
Risks:
* | Loss | of | good | supplier.
Opportunities:
* | Maintain | good | relationship | with | good | suppliers.
* | Pro-actively | review | supplier | performance
* | Refer | to | “Procurement” | and | “Business | Risk | (financial)” | row | above
International | Rope | Access | Trade | Association | (IRATA):
Independent | verification | that | Absafe | conducts | a | core | business | activity, | i.e. | rope | access | work, | to | the | highest | possible | internationally | recognised | standards.
Risks:
* | Non-compliance | with | the | ICOP.
* | Non-compliance | with | audit | requirements.
Opportunities:
* | International | recognition | and | acceptance
* | Demonstrates | Absafes | commitment | to | safe | work | and | safe | development | of | the | industry.
* | Managed | through | current | processes
* | Continued | ISO | implementation | assists | to | meet | requirements.
Painting | Contractor | Certification | Program | (PCCP):
Independent | verification | that | Absafe | conducts | a | core | business | activity, | industrial | painting | and | coating | works, | to | a | recognised | industry | standard.
Risks:
* | Non-compliance | with | audit | requirements.
Opportunities:
* | National | recognition | and | acceptance
* | Demonstrates | Absafes | commitment | to | QSE.
* | Makes | Absafe | eligible | for | more | tenders.
* | Continued | ISO | implementation | assists | to | meet | requirements.
Australasian | Concrete | Repair Association | (ACRA) | and | Australasian | Corrosion | Association | (ACA)
Independent | verification | that | Absafe | conducts | a | core | business | activity, | corrosion | control, | concrete | repair, | to | a | recognised | industry | standard.
Risks:
* | Non-compliance | with | industry | standards.
* | Insufficient | training | and | awareness
Opportunities:
* | Demonstrates | Absafes | commitment | to | the | industry.
* | Provides | networking | and | business | opportunities.
* | Makes | Absafe | more | appealing | to | customers.
* | Continue | ongoing | training.
* | Continue | conference | attendance | and | networking | events.
WorkSafe | Victoria | (and | equivalent | in | other | jurisdictions):
Compliance | OHS | legislation; | safe | and | healthy | workplaces; | compliance | with | workers' | compensation, | rehabilitation | and | RTW | legislation.
Risks:
* | Non-compliance, | prosecution.
* | Safe | workplace | not | maintained.
Opportunities:
* | Maintenance | of | safe | workplace.
* | Industry | and | client | recognition.
* | No | reportable | incidents.
* | Refer | to | “Understanding | Compliance | Requirements” | and | “Project | QSE” | above.
EPA | Victoria | (and | equivalent | regulators | in | other | jurisdictions):
Compliance | with | Environmental | legislation, | not | to | pollute | environment | (air, | water, | soil, | groundwater).
Risks:
* | Non-compliance, | prosecution.
* | Pollution | event.
Opportunities:
* | Good | environmental | performance.
* | Industry | and | client | recognition.
* | Include | awareness | of | pollution | control | requirements | in | training/ | communication | programs.
* | No | reportable | pollution | events.
* | Refer | to | “Understanding | Compliance | Requirements” | and | “Project | QSE” | above.
Members | of | the | public | who | may | be | affected | by | Absafe's | activities:
They | are | protected | from | safety | hazards
Risks:
* | Accident | or | injury.
* | Upset | member | of | public
* | Damage | to | property | or | neighbouring | premises.
* | Impact | to | surrounding | business | owners.
* | Don’t | hold | appropriate | insurance
* | Cost | of | insurance | premiums
Opportunities:
* | Improved | understanding | and | engagement | processes.
* | Better | mitigation | of | risks | towards | the | public | and | negative | impacts | to | Absafe.
* | Clear | communication | with | business | owners | and | the | public.
* | Communicate | to | staff | and | supervisors | – | the | importance | of | reducing | risk | to | the | public.

## Sheet8
Risk, | Opportunity | and | Objectives | Register
Issue/ | Expectation/ | Source
Risk/ | Opportunity
Related | Objectives
Further | Actions
Who
By | When
Workflow | program
Risks:
* | Inconsistent | work | levels
* | Cashflow | – | regular | income, | forecasting
* | Resources | unavailable | to | schedule | works.
Opportunities:
* | Marketing | resource | to | increase | consistency | of | workflow
* | Business | development
* | Target | areas
* | Identify | and | engage | marketing | resource
* | Staff | training | – | upskill | in | area | of | business | development | (1% | of | budget)
* | Develop | new | marketing | material.
* | Engage | new | Business | Development
* | Develop | business | development | strategy
* | Forecasting | approach
* | Staff | retention | (refer | below)
* | Microsoft | project | training | for | resource | scheduling
* | Review | lead | report | in | WFM | in | the | Quarterly | Management | meeting
Op's | Manager
New | manager | - | July | 2018
Upskilling | program | – | commenced | by | September | 2018
Staff
Risks:
* | Morale
* | Poor | engagement | and | productivity
* | Loss | of | key | staff/ | skills/ | knowledge.
* | Retention
* | Un-safe | work | environment
Opportunities:
* | Interesting | work
* | Keeping | staff | involved | in | process/ | project
* | Encourage | consultation | and | listening | - | across | all | levels
* | Develop | staff | retention | strategy
* | Better | communication
* | Staff | input | – | encourage | as | part | of | toolbox | talks | and | site | communication
* | Consider | regular | Supervisors | and | Level | 3 | meetings | (and/or | more | group | emails)
* | Unsafe | workplace | – | supervision, | communication, | systems
GM
December | 2018
Understanding | compliance | requirements
Risks:
* | Incur | a | non-conformance
* | Not | controlling | the | job | to | manage | hazards/ | risks | to | requirements
* | Liability
* | Reputational | impact
* | Audit | failure
* | Failure | to | communicate | a | reportable | accidents/incidents | to | external | parties | (e.g. | to | EPA, | IRATA | or | Worksafe)
* | Failure | to | communicate | accidents, | incidents, | hazards | to | internal | parties.
Opportunities:
* | Training
* | Implementing | system(s)
* | Improve | knowledge/ | understanding | of | requirements
* | Commitment | to | achieving | requirements
* | Develop | Communication | or | Training | initiatives | related | to | compliance | (2 | per | annum)
* | Continual | improvement | of | systems
* | Monitoring | of | systems | and | compliance
* | Compliance | results | reviewed | actively | in | management | review | meetings
* | Schedule | internal | audits | of | compliance | management | processes.
* | External | reporting | requirements | identified | in | current | system | (in | management | review | of | incident | form)
Op's | Manager | and | GM
Additional | initiatives | identified | by | Sept | 2018
Customer | requirements | and | needs
Risks:
* | Incur | liquidated | damages,
* | defects | liability,
* | Unable | to | reach | practical | completion
* | Unhappy | customer
Opportunities:
* | Repeat | work | with | customer
* | Cashflow | – | paid | on | time
* | Customer | recommendations
* | Evaluate | options | to | better | capture/ | review | customer | feedback
* | At | least | two | client | feedback | per | month
* | Evaluate | options | to | better | capture/ | review | customer | feedback
* | Improve | awareness | of | supervisors | to | ask | for | feedback | in | project | closure.
* | Establish | project | completion | form
* | BD | to | contact | clients | to | obtain | feedback
Marketing | Manager
End | of | 2018
Cloud | based | systems
Risks:
* | Poor | backup
* | Lack | of | training | in | use
* | Too | many | draft | forms | and | unsubmitted | documents.
* | Downtime
* | Storage | capacity
* | Capability | and | restrictions
* | Security
Opportunities:
* | Improved | training
* | Knowledge | sharing
* | Mobile | access
* | 85% | of | project | documentation | submitted | on | time | within | project
* | Reduce | draft | forms | - | 0% | for | completed | / | closed | out | projects, | 30 | days | from | date | created
* | Improve | training
* | Investigate/confirm | backup | processes
* | At | project | close | out | look | at | forms | and | action | / | submit | all | draft | forms | or | delete | if | form | not | in | use | for | that | project.
* | Quick | over | look | of | all | forms | check | forms | and | template | area | of | Upvise.
Op's | Manager | and | GM
End | of | 2018
Business | risk | (financial)
Risks:
* | Liquidity
* | Cashflow
* | Delays | or | not | getting | paid.
* | Incorrect | invoicing | (as | per | PO)
Opportunities:
* | Process | improvements | to | better | manage | cashflow
* | Set | budgets
* | Invoicing | asap
* | Understand | invoicing | improvement | opportunities
* | Internal | understanding | importance | of | cashflow/ | invoicing
* | Standardise | terms | and | conditions | on | invoices.
* | Invoicing | as | per | PO
* | Cc | General | Manager | for | all | invoices | sent
Project | Staff | awareness | (quality, | safety, | environmental)
Risks:
* | QSE | processes | not | implemented | when | they | need | to | be
* | Not | controlling | the | job | to | manage | hazards/ | risks | to | requirements
* | Liability
* | Reputational | impact
* | Audit | failure
Opportunities:
* | Reputation | as | good | provider
* | Improve | staff | knowledge | and | QSE | understanding
* | Develop | Communication | or | Training | initiatives | related | to | compliance | (2 | per | annum)
* | Develop | training | program | to | improve | QSE | awareness | and | implementation
* | Continue | project | reviews | and | audits | to | identify | improvement | opportunities
* | Operations | Manager | and | Regional | Manager | to | provide | feedback, | instruction | and | continue | monitoring
Op's | Manager | and | GM
Sept | 2018
Procurement
Risks:
* | Incorrect | materials/ | equipment,
* | Over-ordering
* | Project | delays
* | Changing | prices
* | Over | budget
* | Difficulty | sourcing | specified | materials
Opportunities:
* | Increase | productivity | and | minimise | delays
* | Save | money
* | Procurement | improvement | strategy | to | be | developed
* | Understanding | cost/benefit | of | materials | and | equipment.
* | Understanding | specification | and | contract
* | Improve | communication | and | checking | of | current | equipment | with | warehouse | and | logistics | manager
* | Research | product | suitability | and | comparisons | (including | QSE | implications)
GM
December | 2018
Manual | handling
Risks:
* | Injury
* | Down-time
* | Costs | and | insurance | premiums
Opportunities:
* | Safer | work | environment
* | Change | mentality | and | awareness
* | Establish | baseline | (manual | handling | injuries | per | project | hours | worked)
* | Set | target | based | on | baseline | by | March | 2019
* | Training
* | Reinforce | ones’ | self-responsibilities | and | supporting | each | other
Op's | Manager
March | 2019
Communication | within | the | business
Risks:
* | Loss | of | internet | access | (ADSL2)
* | Communication | – | important | information | not | passed | on | or | understood
* | Communication | not | consistent | with | internal | process | and | protocol
Opportunities:
* | Consider | procedure/ | processes | for | back-up | system | in | event | of | communication | failure
* | Evaluate | 4G | backup | options
* | Evaluate/identify | further | internal | meeting | forums/ | processes | to | facilitate | improved | communication
* | Evaluate | need | for | other | internal | meetings
* | Improve | use | and | interaction | of | group | emails
* | Evaluate | 4G | backup | options
* | Recording | information | (detailed | daily | labour, | project | sign-off | sheet)
* | All | staff | to | complete | general | Absafe | staff | induction
GM
End | of | December | 2018
Tenders
Risks:
* | Not | aware | of | tender | opportunity
* | Non-complying | submission
* | Inaccurate | pricing | and | approach
* | Cost | of | tendering
* | Management | of | RFIs
Opportunities:
* | Improve | tender | opportunity | discussion | (bid/ | no-bid | approach)
* | Marketing, | business | development | and | networking
* | Initiate | a | tender | review | process
* | Allocate | tender | management | responsibility
* | Network | event | (attend | at | least | one | per | quarter)
* | Marketing | and | BD | resource
* | Increase | marketing | and | trade | shows/ | conferences
* | Initiate | a | tender | review | process
* | Allocate | tender | management | responsibility
Marketing | and | BD | Manager
December | 2018
Clients, | including | workers | at | client | sites:
Fair | and | transparent | business | relationships; | competent | workers, | supervision | and | equipment | to | complete | works | in | a | safe, | environmentally | sustainable | and | timely | fashion | in | accordance | with | agreed | business | terms.
Risks:
* | Job | delivery | not | meeting | expectations
Opportunities:
* | Use | systems | to | capture | organizational | knowledge
* | Mobile | access | to | company/project | information
* | Managed | through | current | business | reporting, | management | and | oversight | processes.
* | No | further | action | required | (apart | from | continued | implementation | of | systems).
Absafe | Pty | Ltd | Shareholders | and | Directors:
Profitable | and | sustainable | business, | good | corporate | governance, | appropriate | management | of | risk | (financial, | legal | / | compliance, | OHS, | environmental, | reputational).
Risks:
* | Projects | not | delivered | to | expectations.
Opportunities:
* | Continual | improvement | of | systems | and | processes
* | Continual | improvement | of | systems | and | processes
Employees:
Profitable | and | sustainable | business, | job | security, | fair | remuneration, | safe | and | healthy | workplace, | positive | work | environment
Risks:
* | Unstable | workflow | or | other | factors | reduce | retention | rates.
Opportunities:
* | Steady | work, | good | communication | – | assist | in | maintaining | staff.
* | Refer | to | “Staff” | row | above
Subcontractors | and | their | workers:
Fair | and | transparent | business | relationships, | payment | terms, | safe | and | healthy | workplaces | during | project | works.
Risks:
* | Not | being | able | to | apply | same | level | of | control | to | sub-contractor | activities
Opportunities:
* | Minimise | use | of | sub-contractors | where | possible
* | Maintain | Absafe | staff | member | on-site | with | contractor | at | all | times
* | Continue | to | ensure | Absafe | staff | member | on-site | with | contractor | at | all | times
Op's | Manager
Consider | in | project | planning
Suppliers | of | equipment | and | materials:
Fair | and | transparent | business | relationships, | timely | payment | terms.
Risks:
* | Loss | of | good | supplier.
Opportunities:
* | Maintain | good | relationship | with | good | suppliers.
* | Pro-actively | review | supplier | performance
* | Refer | to | “Procurement” | and | “Business | Risk | (financial)” | row | above
International | Rope | Access | Trade | Association | (IRATA):
Independent | verification | that | Absafe | conducts | a | core | business | activity, | i.e. | rope | access | work, | to | the | highest | possible | internationally | recognised | standards.
Risks:
* | Non-compliance | with | the | ICOP.
* | Non-compliance | with | audit | requirements.
Opportunities:
* | International | recognition | and | acceptance
* | Demonstrates | Absafes | commitment | to | safe | work | and | safe | development | of | the | industry.
* | Managed | through | current | processes
* | Continued | ISO | implementation | assists | to | meet | requirements.
Painting | Contractor | Certification | Program | (PCCP):
Independent | verification | that | Absafe | conducts | a | core | business | activity, | industrial | painting | and | coating | works, | to | a | recognised | industry | standard.
Risks:
* | Non-compliance | with | audit | requirements.
Opportunities:
* | National | recognition | and | acceptance
* | Demonstrates | Absafes | commitment | to | QSE.
* | Makes | Absafe | eligible | for | more | tenders.
* | Continued | ISO | implementation | assists | to | meet | requirements.
Australasian | Concrete | Repair Association | (ACRA) | and | Australasian | Corrosion | Association | (ACA)
Independent | verification | that | Absafe | conducts | a | core | business | activity, | corrosion | control, | concrete | repair, | to | a | recognised | industry | standard.
Risks:
* | Non-compliance | with | industry | standards.
* | Insufficient | training | and | awareness
Opportunities:
* | Demonstrates | Absafes | commitment | to | the | industry.
* | Provides | networking | and | business | opportunities.
* | Makes | Absafe | more | appealing | to | customers.
* | Continue | ongoing | training.
* | Continue | conference | attendance | and | networking | events.
WorkSafe | Victoria | (and | equivalent | in | other | jurisdictions):
Compliance | OHS | legislation; | safe | and | healthy | workplaces; | compliance | with | workers' | compensation, | rehabilitation | and | RTW | legislation.
Risks:
* | Non-compliance, | prosecution.
* | Safe | workplace | not | maintained.
Opportunities:
* | Maintenance | of | safe | workplace.
* | Industry | and | client | recognition.
* | No | reportable | incidents.
* | Refer | to | “Understanding | Compliance | Requirements” | and | “Project | QSE” | above.
EPA | Victoria | (and | equivalent | regulators | in | other | jurisdictions):
Compliance | with | Environmental | legislation, | not | to | pollute | environment | (air, | water, | soil, | groundwater).
Risks:
* | Non-compliance, | prosecution.
* | Pollution | event.
Opportunities:
* | Good | environmental | performance.
* | Industry | and | client | recognition.
* | Include | awareness | of | pollution | control | requirements | in | training/ | communication | programs.
* | No | reportable | pollution | events.
* | Refer | to | “Understanding | Compliance | Requirements” | and | “Project | QSE” | above.
Members | of | the | public | who | may | be | affected | by | Absafe's | activities:
They | are | protected | from | safety | hazards
Risks:
* | Accident | or | injury.
* | Upset | member | of | public
* | Damage | to | property | or | neighbouring | premises.
* | Impact | to | surrounding | business | owners.
* | Don’t | hold | appropriate | insurance
* | Cost | of | insurance | premiums
Opportunities:
* | Improved | understanding | and | engagement | processes.
* | Better | mitigation | of | risks | towards | the | public | and | negative | impacts | to | Absafe.
* | Clear | communication | with | business | owners | and | the | public.
* | Communicate | to | staff | and | supervisors | – | the | importance | of | reducing | risk | to | the | public.